# SWM PLAN CHECKLIST of INFORMATION TO BE COLLECTED

for Developing Micro-Management Plans                                       7.4.2000

## GIS of entire City

- Map all the slums, authorised or not

- Map all Health-Ward Offices

- Map all waste recyclers, wholesale and retail, with types of waste

- Map all parks and open spaces (for decentralised composting)

- Map all stables, preferably with number of animals

- Map all health-care establishments

- Map all eateries, mantapas and halls

- Map all major open storm-water drains and lakes

- Map and list all major Institutions

- Map all Civic amenity areas and parks

- Map all known Residents’ Assns + major Multistorey bldgs

- Map all Central Govt, Rly and Defence bldgs or areas

- Map all high-tension lines, for Bijli-bagh greenery

- Map all weigh-bridges

- Map all Markets and Shopping Complexes

- Map all Railway or Bus stations and theatres

- Fmap major hawker-congregation areas

## Primary Collection of WET Waste

- Get maps of every Health Ward

- Get total road lengths per Health Ward

- Plot the Ward Office, with its site area + built-up area

- Plot all BCC and State Govt  properties

- Plot all possible handcart parking points

- Plot route of every handcart in each of 60 Health Wards

- Rationalise routes of handcarts within the Health Ward

- Time and space plotting, to plan for moving-truck pickups

- Routing theory to plan  inner-city pickup routes by trucks

- Get Ward-wise numbers of BCC and/or contract sweepers

- Plan pin-point beats for each sweeper, for AM and PM shifts

- Plan for adequate pinpoint sweepers for each Ward

- Mark “pin-pint beats” on the street map.

- Primary Collection of DRY Waste

- List all waste-buyers and their waste-picker suppliers

- List all itinerant waste-purchasers and what they buy

- List all waste whole-salers and their specialties

- Try to organise all the retailers and wholesalers

- Identify and list all non-recyclable packaging

- Try to minimise non-recyclables via waste-prevention rules

- Identify waste-sorting stations (e.g. under flyover corners)

- Hire out handcarts for transport of dry wastes if reqd

- Secondary Transport, BCC Trucks + Contract Trucks

- Follow every truck all day for a week

- Map its present route, with timings, inner-city

- Map cleared and uncleared bins, Monday to Sunday

- Map its present destination and area, for sanitising

- Note travel time from last pickup to dropoff, to rationalise destinations

- Ascertain their night-parking places

- Get all mileometers working

- Start log-book for each driver

- Routing theory to decide unloading destinations per Ward

- Map what storm-drains are passed en-route

- Map any weigh-bridges en-route.

- Present Disposal Sites

- Monitor lorry No and arrival time

- Assess unloading and turnaround time

- Assess load quantity (half, full, over-full)

- Assess area and waste stockpiles to be treated

- Sanitising Present Disposal Sites

- Dust with sanitiser upon unloading

- Explore possible slurry-treatment enroute

- Identify nearest non-potable water-source

- Assess cost of tankers for bio-treatment

- BCC to seek KCDC help for this (AHP has contacted them)

- BCC to invite private bids for sanitising work

- Consider sanitising major nuisance-points in city thru pvt parties

- Plans for Local Processing:  Decentralised

- List all the major Institutions that should be required to become zero-garbage campuses

- List all very-large multistory bldgs that can and/or should do this

- Consider one-week composting in the Ward before pickup to rural site

- Estimate area required and available for Ward-wise decentralising

- List resource persons available for this, maybe from existing routes

- Plans for Final Processing: Centralised

- BCC to first invest in site developments and infrastructure: (wall, internal roads, paved yard for composting

- Invite plant + eqpt and process bids from existing experienced parties

- Evaluate Technical Bids before opening Financial Bids

- Assess cost-benefits of each bid based on royalty offered

- BCC to seek lowest-cost funds, to make each site self-financing

- Identify interested parties for composting at Kanahalli 29a (-do-)

- BCC to seek airport clearances for Medi-Agrahara site (8 km from Jakkur and Jalahalli airports)

- PERT Chart for Final Processing

- Plan for Final Disposal

## PERT for Final Disposal

## Debris Management Plan

- BCC to finalise approach and exit roads for 3 quarry-sites:

Kaval-Byrasandra, Lakkasandra and Sarakki

- BCC to depute SWM engrs for traffic mgt and qty mgt at these

- Prepare a draft Debris Mgt Plan for approval at (or before?) May 20.

- Write a Press Note re. Available sites and mgt plans at sites

- Storm-Drain and Silt management

- Estimate drain-wise volumes from width and depth

- Decide how to dredge out silt-traps in full-flowing storm-drains

- Include destination-quarry in every desilting tender and ENFORCE this

- Have a debris-quarry manager at each destination site to manage placemt

# 14   Sewage in Storm-Water Drains

- Estimate cost of desilting each major drain

- Consider moving bed-silt to side-walls and planting for sewage treatmt

- Consider Nala-baghs for in-situ sewage treatment

- Consider duckweed aquaculture with help from CIFA Blr + Bhubaneswar

- MAP EVERY INFLOW POINT into every drain while desilting

- BCC to issue notices to every traceable offender

- BCC to invite applications for sewage connections at discount rates till some cutoff date.   Double the connection charges thereafter.

- Hospital Waste Management

- BCC to calculate cost of own collection+transport+incineration at Seegehalli 7a (off Magadi Rd)

- Work closely with KSPCB which has received several bids

- BCC to publicise its own rates + KSPCB’s offers

- Invite IMA and Nursing Home Assn etc proposals for self-mgt of collection services including transport and disposal at Seegehalli site

- Initiate dialogue in media for transparency and acceptance of charges

- Domestic Hazardous Waste

- BATF to invite BPL etc to suggest used torch-cell recycling or take-back

- Major stores to invite their customers to return clean used plastic bags via a drop-off bin at each store, for reuse and waste minimisation

- Find participating stores for “hundi” for broken glass

- Paint distributors to technically and financially support safe disposal / recycling or take-back of their paint cans, and inform which contain lead or cadmium or materials hazardous for landfilling

- BCC to consider a ban on Styrofoam / Thermocole packaging and use in window displays and a take-back policy for all white-goods and IT using it

- BATF to invite IT companies to display alternate packaging like folded-cardboard, bubble-plastic films, popcorn-packets etc

- Consider biodegradable plastic bag usage                        SWM Plan Checklist